## Gantt Chart
	2022-yardas-ms				12%
	ARFC-NPRE-UIUC
	mmunk2, oyardas2		Tuesday, February 15, 2022

										01					02					03					04					05					06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25					26
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Dec-21		Jan-22					Feb-22					Mar-22					Apr-22					May-22					Jun-22
			30-Dec-2021	97	14-May-2022	12%	136			30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28
	Literature Review	[name]	30-Dec-2021	18	24-Jan-2022	29%	26	9	27
	Preliminary research and reading
	Reading and notetaking	[name]	30-Dec-2021	14	18-Jan-2022	34%	20	4	10
	OpenMC and Serpent	[name]	30-Dec-2021	4	04-Jan-2022	50%	6	2	2
	SaltProc	[name]	05-Jan-2022	3	07-Jan-2022	75%	3	2	1
	Software development	[name]	10-Jan-2022	3	12-Jan-2022	40%	3	1	2
	Reactor analysis	[name]	13-Jan-2022	3	17-Jan-2022	0%	5	0	3
	Burnup analysis	[name]	18-Jan-2022	3	20-Jan-2022	0%	3	0	3
	Secondary review of current matierials
	Citations	[name]	18-Jan-2022	1	18-Jan-2022	5%	1	0	1
	Summarize goals, applicability, results	[name]	18-Jan-2022	5	24-Jan-2022	0%	7	0	5
	Enable OpenMC support in SaltProc	[name]	18-Jan-2022	19	11-Feb-2022	44%	25	36	48
	Refactor classes	[name]
	App	[name]	18-Jan-2022	18	10-Feb-2022	100%	24	18	0
	Simulation	[name]	18-Jan-2022	18	10-Feb-2022	100%	24	18	0
	Test	[name]	18-Jan-2022	18	10-Feb-2022	0%	24	0	18
	Write OpenMC classes	[name]
	DepcodeOpenMC	[name]	24-Jan-2022	15	11-Feb-2022	5%	19	0	15
	Tests for OpenMC classes	[name]	24-Jan-2022	15	11-Feb-2022	0%	19	0	15
	Reactor analysis	[name]	24-Jan-2022	31	07-Mar-2022	0%	43	0	2
	Input file Setup	[name]	14-Feb-2022			0%
	Cross section library preprocessing	[name]
	Serpent2	[name]	01-Feb-2022	2	02-Feb-2022	0%	2	0	2
	OpenMC	[name]	01-Feb-2022	2	02-Feb-2022	0%	2	0	2
	Geometry files	[name]
	Serpent2	[name]	24-Jan-2022	5	28-Jan-2022	0%	5	0	5
	OpenMC	[name]	24-Jan-2022	5	28-Jan-2022	0%	5	0	5
	Material files	[name]				0%
	Serpent2	[name]	24-Jan-2022	5	28-Jan-2022	0%	5	0	5
	OpenMC	[name]	24-Jan-2022	5	28-Jan-2022	0%	5	0	5
	Settings files	[name]				0%
	Serpent2	[name]	24-Jan-2022	5	28-Jan-2022	0%	5	0	5
	OpenMC	[name]	24-Jan-2022	5	28-Jan-2022	0%	5	0	5
	Depletion	[name]
	OpenMC	[name]	28-Jan-2022	5	03-Feb-2022	0%	7	0	5
	SaltProc input files	[name]	28-Jan-2022	2	31-Jan-2022	0%	4	0	2
	Run simulation cases	[name]	12-Feb-2022	7	21-Feb-2022		10	0	7
	Proccess data and make figures	[name]	15-Feb-2022	15	07-Mar-2022		21	0	15

	Thesis writing	[name]	30-Dec-2021	-31820	30-Dec-1899	12%	-44559	0	0
	Github Repo for thesis	[name]	30-Dec-2021			100%
	Pre-results writing	[name]	24-Jan-2022			58%
	Background	[name]	30-Dec-2021	18	24-Jan-2022	80%	26	14	4
	Motivation	[name]	30-Dec-2021	18	24-Jan-2022	80%	26	14	4
	Software	[name]	30-Dec-2021	7	07-Jan-2022	13%	9	0	7
	SaltProc	[name]	30-Dec-2021	4	04-Jan-2022	15%	6	0	4
	Serpent2	[name]	30-Dec-2021	4	04-Jan-2022	1%	6	0	4
	OpenMC	[name]	05-Jan-2022	3	07-Jan-2022	25%	3	0	3

	Post-results writing	[name]	14-May-2022			1%
	Methods	[name]	30-Dec-2021	18	24-Jan-2022	1%	26	0	18
	Results	[name]	08-Mar-2022	49	14-May-2022	1%	68	0	49
	Analysis	[name]	18-Jan-2022	84	14-May-2022	1%	117	0	84
	Conclusions	[name]	18-Jan-2022	18	10-Feb-2022	1%	24	0	18
	SaltProc	[name]	18-Jan-2022	18	10-Feb-2022	1%	24	0	18
	Serpent2	[name]	18-Jan-2022	18	10-Feb-2022	1%	24	0	18
	OpenMC	[name]	18-Jan-2022	18	10-Feb-2022	1%	24	0	18

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		1/1/14
		3/4/14
		4/18/14
		4/20/14
		4/25/14
		5/1/14
		6/10/14
		8/15/14
		12/8/14
		12/25/14